CHART 2 – MODEL FOIP REQUEST (Third Party Notice Required)

| Timelines - Calendar Days | Timelines - Working Days | Functional Area Responsible | Key Tasks | Milestones | Manual References | Do's and Don'ts |
| --- | --- | --- | --- | --- | --- | --- |
|  | Before formal request is logged | AU Staff/Departments | Upon receipt of FOIP Request date stamp. Attach request to the envelope or enclosure that included the request. Forward request to FOIP Office. |  |  | Do ensure processing of incoming mail completed daily and FOIP request(s) forwarded to Office of the President ASAP. |
|  |  | Office of the President | Upon receipt of FOIP request will date stamp request and forward to FOIP Office. |  |  |  |
|  |  | FOIP Office | Receive FOIP request and date stamp request. Log receipt of request. Review FOIP request to determine if information is available routinely or is a formal access request. If the information is not available through routine release processes, continue handling following the formal FOIP request procedures. |  | 3.3 Receiving Request/Defining Request/Assisting Applicant 1.9 Routine Access | Do provide information through routine channels. |
| THIRTY DAY CLOCK STARTS 30 Calendar Days to Respond Maximum of 22 Working Days to Respond |
| (Day 1) | Day 1 | FOIP Office | Review and define request. Confirm request to records covered by Act. Contact applicant to define and clarify request if necessary. Is it a continuing request? Is request complete - initial fees paid? Decide if request should be transferred to another public body. |  | 3.3 Receiving Request/Defining Request/Assisting Applicant 3.3 Transferring a Request | Do assist the applicant to define the request. Do clarify what is wanted. Do inform the applicant about the process & about the structure. Do obtain other public body's consent to transfer. |

| Timelines - Calendar Days | Timelines - Working Days | Functional Area Responsible | Key Tasks | Milestones | Manual References | Do's and Don'ts |
| --- | --- | --- | --- | --- | --- | --- |
| (Day 1) Con't | Day 1 Con't | FOIP Office | Make necessary log entries. Complete necessary forms. Create central request file. |  | 3.3 Tracking & Reporting |  |
|  |  |  | Send acknowledgment to applicant. Notify applicant if transferred. |  | 3.3 Receiving Request/Defining Request/Assisting Applicant 1.6 Custody or Control; 3.3 Transferring a Request | Do keep applicant informed. Do obtain other public body's consent to transfer. |
|  |  |  | . | End of 1st working day: Request logged |  |  |
| (Day 2) | Day 2 | FOIP Office | Identify records. Identify staff/office who may custody or control of the records. Contact designation staff to search and locate requested records. Forward necessary forms to staff and/or offices. |  | Processing Request 1.6 Custody or Control; | Don't share personal information about the applicant except on "need to know" basis. |
|  |  |  |  | End of 2nd working day: the request defined, records identified, staff/office(s) contacted. |  |  |
| (Days 2–8) | Days 2 - 6 | Staff/Office(s) | Search for and retrieve records. | End of 4th working day: records retrieved. | 3.4 Locating Records | Do search for all relevant records-including working and electronic files. Do make all reasonable efforts to locate records. |

| Timelines - Calendar Days | Timelines - Working Days | Functional Area Responsible | Key Tasks | Milestones | Manual References | Do's and Don'ts |
| --- | --- | --- | --- | --- | --- | --- |
| (Days 2–8) | Days 2 - 6 | Staff/Office(s) | Report results of records search to FOIP Coordinator. | End of 4th day: results reported to FOIP Coordinator. |  | Do attempt to determine if records exist in other program areas or other public bodies. Do keep accurate & complete documentation of records search. |
|  |  | Staff/Office(s) | Copy retrieved records. | End of 5th working day: Records copied. |  | Do update applicant on progress of request. |
|  |  | FOIP Office/Designated Authority/Staff | Preliminary assessment (includes following tasks): - Consider fees. Send fee notice if applicable. - Collect fee deposit if applicable. Suspend processing until deposit received. | End of 6th working day: Decision on fees. Collect deposit if applicable. | 3.4 Preliminary Assessment 3.4 Fees | Don't use original records during review & severing. Do consider any request for fee waiver. |
| Clock stops until fee deposit received |
|  |  | See chart 2 for model request showing third party notice time limits and extension | Preliminary Assessment: - Third party notices required? (Last day on which it is possible to give 3rd party notice & respond within 30 days from receipt). |  | 5. Third Party Notice | Do send third party notices as early as possible. |
| (Day 8) | Day 6 | FOIP Office | Send notices to third party & applicant. | End of 6th working day: Third party notices sent. |  | Do notify applicant of third party consultations & date by which decision will be made. |
| Section 29 Time Limit in Effect 30 Calendar Days from date of 3rd party notice to respond Maximum of 22 Working Days from date of 3rd party notice to respond |

| Timelines - Calendar Days | Timelines - Working Days | Functional Area Responsible | Key Tasks | Milestones | Manual References | Do's and Don'ts |
| --- | --- | --- | --- | --- | --- | --- |
| (Days 1–6) | Days 1–6 | Office/Staff/Designated authority/FOIP Office | Consider reassignment to another office. |  | 3.4 Processing request |  |
|  |  |  | Consider creation of a record. |  | 3.4 Creating a new record |  |
|  |  |  | External consultations required? Initiate consultations/consideration of responses. |  |  |  |
|  |  |  | Internal consultations required? Initiate consultations/consideration of responses. |  |  |  |
| (Days 1–19) | Days 1–19 | Designation Authority/ FOIP Office | Detailed (line by line) review. Apply exceptions. | End of 19th working day: Detailed review completed | Line by Line Review of Records 4. Exceptions to Right of Access 4. Mandatory and Discretionary Exceptions | Do keep designated authorities/staff informed as necessary. Do keep accurate and complete documentation of review. Do update applicant on progress of third party & other consultations. |
| (Day 7) | Day 5 | FOIP Office | Final decision on transfer. (Last day on which request can be transferred to another public body. 15 days from date request received). | End of 5th working day.: Final decision on transfer. | 3.3 Transferring a Request | Do notify applicant if request is transferred. |
| (Day 20) | Day 15 | FOIP Office | Responses received from third party. | End of 15th working day: (20th calendar day) from date of notice. Deadline for response from third parties. | 5. Third Party Notification and Notice |  |
| (Days 17–25) | Days 13-19 | FOIP Office | Third party consultations / Consideration of responses (Ongoing). Consider need for extension to complete 3rd party consultations. |  | 5. Third Party Notification and Notice 3.3 The Response Timetable |  |

| Timelines - Calendar Days | Timelines - Working Days | Functional Area Responsible | Key Tasks | Milestones | Manual References | Do's and Don'ts |
| --- | --- | --- | --- | --- | --- | --- |
| (Day 26) | Day 20 | FOIP Office | Final analysis of reviews & recommendations. |  | 3.4 Line by Line Review of Records |  |
|  |  |  | Prepare final recommendations. | End of 20th working day: FOIP Coordinator's recommendations ready. | Line by Line Review of Records 4. Mandatory and Discretionary Exceptions | Do keep accurate and complete documentation of decisions. |
| (Day 29) | Day 21 | FOIP Office | Make final decision on response to request. | End of 21st working day: Final decision on response. | 3.4 Line by Line Review of Records 4. Mandatory and Discretionary Exceptions |  |
| (Day 30) | Day 22 | FOIP Office | Sever records. |  | 3.4 Severing Information | Don't sever original records. |
|  |  |  | Prepare records for applicant. | End of 22nd working day: Severing completed; response ready | 3.5 Responding to a FOIP Request | Do maintain a record of response and copies of severed records for future use |
|  |  |  | Send response letter to applicant. (Either regarding balance of fees or enclosing copies of records, if all fees paid.) Last day on which notice of extension can be sent. | End of 22nd working day: response letter sent | 3.5 Responding to a FOIP Request 3.3 The Response Timetable | Do explain severing decisions to applicant. Do make decision on extension as early as practicable. |
| (Day 30) | Day 22 | FOIP Office | Collect fee balance owing (if applicable). No further processing until fee balance received. |  | 3.4 Fees | Do consider any request for fee waiver. |
| Clock stops until fee balance received |
| Final response letter to applicant |  | FOIP Office | Set date for access to records, if by examination on-site or send copies to applicant. |  | 3.5 Responding to a FOIP Request |  |